## Slide 1: Understanding Earned Value Analysis

## Slide 2: How is project health measured?
Project Manager evaluates project’s triple constraint of scope, time and cost
Key Questions
  Is the project performing to budget?
  Is the project on schedule to deliver the agreed scope?
Typically Summarize Project Health using Green, Yellow, Red Status (Traffic Light Reporting)

## Slide 3: Problems with the Traffic Light status approach
Subjective to interpretation and influence
No objective measurement to guide Project Health
A project can report green and suddenly turn red before a few days before the launch
A project can report red and be rationalized to green or yellow without any objective data
No prior indicators to problems

## Slide 4: Apply Earned Value Analysis
Earned Value Analysis (EVA)
  Earned Value Analysis is an objective method to measure project performance in terms of scope, time and cost
  Use EVA metrics are used to measure project health and project performance

## Slide 5: Earned Value Characteristics
Point in Time Evaluation
How much work did you PLAN to complete? (Planned Value)
How much work did you ACTUALLY complete? (Earned Value)
How much did you spend to complete the work? (Actual Cost)

## Slide 6: EVA Example
A $10,000 software project is scheduled for 4 weeks.
At the end of the third week, the project is 50% complete and the actual costs to date is $9,000
    Planned Value (PV) = $7,500
    Earned Value (EV) = $5,000
    Actual Cost (AC) = $9,000

## Slide 7: What is the project health?
  Schedule Variance
  = EV – PV = $5,000 – $7,500 = - $2,500
  Schedule Performance Index (SPI)
  = EV/PV = $5,000 / $7,500 = .66
  Cost Variance
  = EV – AC = $5,000 - $9,000 = - $4,000
  Cost Performance Index (CPI)
  = EV/AC = $5,000 / $9,000 = .55
  Objective metrics indicate the project is behind schedule and over budget.
  On-target projects have an SPI and CPI of 1 or greater

## Slide 8: Forecasting Costs
If the project continues at the current performance, what is the true cost of the project?
Estimate At Complete
  = Budget At Complete (BAC) / CPI
  = $10,000 / .55 = $18,181
  At the end of the project, the total project costs will be $18,181

## Slide 9: Establish Ranges to Guide Traffic Light Status
Traffic Light status is useful in conveying overall project with one color
Establish objective SPI and CPI ranges to determine the true project color.
  Green [1.0 - .95]
  Yellow [.94-.85]
  Red [.84, 0]

## Slide 10: Earned Value Summary
Earned Value is an objective method of determining project performance instead of subjective approaches
Apply Earned Value enforces the project discipline of tracking project actual performance against baseline costs and dates
Estimate at Complete calculation can forecast true project costs based on project performance