## Slide 1: Earned Value Management - Agile
Karthik Mani

## Slide 2: Agenda
EVM – Introduction
Agile EVM – Scrum project
Use Case
Analysis Report
Closer look
Portfolio EVM Scrum on Scrum - Next
QA

## Slide 3: EVMS
What is EVMS
Why do we need EV
How do we do EV

## Slide 4
“Have we done what we said we’d do?”
Knowing where you are on schedule?
Knowing where you are on budget?
Knowing where you are on work accomplished?

## Slide 5: Agile
Why is this different?
  EV is not different
  Terminology and assumptions may look different
  PV, EV, CPI and SPI are same
  Instead of WBS, Iterations and stories

## Slide 6: What we need
The total story points completed
The number of Iterations completed
The total Actual Cost
The total story points added to or removed from the release plan.

## Slide 7: Example – Story board
 | Features/CR/Defects | Status | Estimate | Completed (storypoints) | Actual Cost (1000s dollars)
Iterations |  |  | (storypoints) |  | 
Iteration1 | Create Login screen | Completed | 10 | 10 | 15
 | Add AD authentication to login | Completed | 20 | 20 | 30
 | Display items with rates | Completed | 10 | 10 | 20
Iteration2 | Allow user to register |  | 20 |  | 
 | Authenticate registered users |  | 20 |  | 
Iteration 3 | Setup payment options |  | 10 |  | 
 | Add partial payment options |  | 5 |  | 
 | Add transaction gateway to payment center |  | 25 |  | 
 | Print payment receipt |  | 20 |  | 
Iteration 4 | Allow user to provide feedback and ratings |  | 10 |  | 
 | Add order history to user profile |  | 10 |  | 
 | Save user preference options |  | 20 |  | 
 | Allow user to connect social networking |  | 20 |  | 
 | Totals |  | 200 | 40 | 65
No. of Iterations Planned | 4
No of iterations completed | 1
Budget | 175000

## Slide 8: Analysis - Results
Expected completion | 25%
Planned Value (PV) | 43750
Actual completion | 20%
Earned Value (EV) | 35000
CPI | 0.538462
SPI | 0.8
Estimate to complete the project | 325000
Estimated iteration to complete | 5

## Slide 9: Let’s take a look

## Slide 10: Values
Expected completion | Number of completed iterations divided by the number of planned iterations | 0.25 | 25%
Planned Value (PV) | Expected Percent Complete multiplied by the Total Budget | 25% * 175000 | 43750
Actual completion | Total number of story points completed divided by the total number of story points planned | 0.20 | 20%
Earned Value (EV) | Multiplying Actual Percent Complete by the Total Budget | 20% * 175000 | 35000
CPI | Dividing Earned Value by the Actual Cost | 35000/65000 | 0.54
SPI | Dividing the Planned Value into the Earned Value | 43750/35000 | 0.8
Estimate to complete the project | Divide the Total Budget by the Cost Performance Index | 175000/.54 | 325000
Estimated iteration to complete | Dividing the SPI into the Planned Iterations | 4/.8 | 5

## Slide 11: Report/Dashboard

## Slide 12: Portfolio EVM